## Slide 1
RLCA
Architectural Review Board
February 14, 2002

## Slide 2: Agenda
Change Highlights
  OCD – Antonia
  SSRD – Mike
  SSAD – Pallavi
  LCP – Antonia
  FRD – Mike
Iteration 1 Development Breakdown/Plan – Lucy
Development Status to Date – Chris
Risks Moving Forward – Mike

## Slide 3: OCD Changes
New Client and Maintainer
OCD 4.3 Proposed System Capabilities
  More descriptive capabilities
  Updated Rose Model

## Slide 4: Agenda
Change Highlights
  OCD - Antonia
  SSRD – Mike
  SSAD – Pallavi
  LCP – Antonia
  FRD – Mike
Iteration 1 Development Breakdown/Plan – Lucy
Development Status to Date – Chris
Risks Moving Forward – Mike

## Slide 5: Requirements Changes
Added COTS Versions
  Apache v1.3
  Java v1.2
  Tomcat v4.0
  MySQL v3.23
Added Language Requirement for Java
Added Java Coding Standard Requirement
Added GUI Color Scheme Requirement

## Slide 6: Agenda
Change Highlights
  OCD - Antonia
  SSRD – Mike
  SSAD – Pallavi
  LCP – Antonia
  FRD – Mike
Iteration 1 Development Breakdown/Plan – Lucy
Development Status to Date – Chris
Risks Moving Forward – Mike

## Slide 7: SSAD Changes
No major changes to the document
There were some minor diagram changes to:
  Make descriptions of the system more accurate
  Keep the SSAD consistent with the MBASE guidelines
  Preserve data integrity with in the document and with other documents
These changes affected the following sections of the document: 2.3, 3.1, 3.2, 3.3, 3.4, 3.5
  Captured in the change summary section of SSAD

## Slide 8: Agenda
Change Highlights
  OCD - Antonia
  SSRD – Mike
  SSAD – Pallavi
  LCP – Antonia
  FRD – Mike
Iteration 1 Development Breakdown/Plan – Lucy
Development Status to Date – Chris
Risks Moving Forward – Mike

## Slide 9: LCP Changes
New Team
  Organization chart
  Roles and responsibilities
Updated Dates
  Changed all TBD to concrete dates

## Slide 10: LCP Changes (cont.)
Project Archive
  Team web site and ClearCase structure
  Updated all relevant URL references
COCOMO Run II
  Estimate analysis

## Slide 11: LCP Changes (cont.)
Risk List
  New risks introduced in CS577b
  Risk Management Plan
Quality Management Plan
  Assessment Activities History
  MBASE v.2.3.6c compliant

## Slide 12: Agenda
Change Highlights
  OCD - Antonia
  SSRD – Mike
  SSAD – Pallavi
  LCP – Antonia
  FRD – Mike
Iteration 1 Development Breakdown/Plan – Lucy
Development Status to Date – Chris
Risks Moving Forward – Mike

## Slide 13: Feasibility Rationale
Costs
  67 man-hour weeks (5 people) for 12 weeks for CS577a class based on data collected
  60 man-hour weeks (5 people) for 10 weeks for CS577b class based on average COCOMO estimate
  1 man-hour weeks for 48 weeks for maintenance
  5 man-hour weeks for 48 weeks for evolutionary capabilities
Savings
  1.5 man-hours per week per project for CS577a/b teams
  0.2 man-hours per week per project for CS577a/b TAs
  9.9 man-hours per project for CS577a/b teams
Benefits
  Improve the quality of a software project
  Reduce long-term project costs and problems
  Improved data quality and accessibility to reviewers

## Slide 14: Return on Investment

## Slide 15: Agenda
Change Highlights
  OCD - Antonia
  SSRD – Mike
  SSAD – Pallavi
  LCP – Antonia
  FRD – Mike
Iteration 1 Development Breakdown/Plan – Lucy
Development Status to Date – Chris
Risks Moving Forward – Mike

## Slide 16: Iteration 1 Development Plan
Schedule
  Target CCD Date of March 25, 2002 – 5 wks total
    4 wks for development/integration
    1 wk for testing
Parallel Tasks (completed by Feb. 27, 2002 – 1.5 wks)
  1) Database – P. Raghavan
    Create and populate database tables.
    Generate SQL statements for JSP’s and forms
  2) User Interface – L. Wong
    Cascading Style Sheet
    Create 6 HTML Pages

## Slide 17: Iteration 1 Development Plan (cont.)
  3) Integration – C. Patel
    Create a DataManager Servlet – use stubs.
    Start converting HTML Page to JSP pages & display data
      ProjectListPage.jsp & ProjectMainPage.jsp
Parallel Tasks (completed by March. 15, 2002 – 2.5 wks)
  1) RiskModel – P. Raghavan
    Separate Java Class - Calculates RE and saves history.
  2) Integration
    HTML to JSP’s, Datamanager & Usermanager - C. Patel
      ListAllPage.jsp, VotingPage.jsp, ProjectSetupPage.jsp
    HTML to JSP & GUI tweaks – L. Wong
      EditRiskPage.jsp

## Slide 18: CCD – From Users Prospective
ProjectLogin.jsp – User logs in (only one project)
ProjectMain.jsp – User see project & stakeholder info
ListAllPage.jsp – User sees list of all project risks (RE values)
VotingPage.jsp – User’s votes will be collected and saved
ProjectSetup.jsp – User can close voting assessment period
– Edit the project name & description
EditRiskPage.jsp – User will ADD, EDIT, DELETE risk items.
– Update mitigation plans per risk.

## Slide 19: Agenda
Change Highlights
  OCD - Antonia
  SSRD – Mike
  SSAD – Pallavi
  LCP – Antonia
  FRD – Mike
Iteration 1 Development Breakdown/Plan – Lucy
Development Status to Date – Chris
Risks Moving Forward – Mike

## Slide 20: Development Status to Date
Obtain Hardware
  Using a Sun Ultra 5 owned by the CSE
    mugu.usc.edu
Prepare Environment
  Installed Solaris 8
    Applied OS security patches
    Have accounts on mugu for Team 15
  Installed development packages
    Tomcat
    Apache
    MySQL

## Slide 21: Development Status to Date (cont.)
Learn Development Packages
  Short learning curve for MySQL, Apache, Tomcat
    Developers are already familiar with required software
Ready to begin development!

## Slide 22: Agenda
Change Highlights
  OCD - Antonia
  SSRD – Mike
  SSAD – Pallavi
  LCP – Antonia
  FRD – Mike
Iteration 1 Development Breakdown/Plan – Lucy
Development Status to Date – Chris
Risks Moving Forward – Mike

## Slide 23: Risks Moving Forward
Web Server Security
  Need a firewall
Maintainer’s Knowledge Base
  Provide information for maintainer to get sufficient training
Testing Time
  Do “risk-driven” testing
Training Participants
  Need to identify with the client
CS577a Deployment Plan
  Supplementary notes supplied at IOC as a separate document

## Slide 24: Risks Moving Forward (cont.)
Lack of Performance Requirements
  “Risk-driven” stress testing
Lack of Understanding of Documentation Process
  Early identification of document needs
IKIWISI GUI Requirement (R30)
  Keep client informed a show early releases
Web Server Memory
  Upgrade coming this semester?
Requirements Creep
  Keep client informed
Use of Database
  Watch development time for slips

## Slide 25: Q & A
Thank You!!