## Slide 1: Objectives For Topic 4
What is the economic aspects in project approach?
  Construction planning, monitoring, and control
  Use of project monitoring metrics
  Assessing and managing project risks

## Slide 2: Topic 4: Project Approach
Metrics
  Monitoring and control
Risk management
  CS 577 Top-10 risks
    Project risk management
    Risk-driven product and process level of detail

## Slide 3: Construction, Transition, and Support Deliverables (CTS)
Construction and Transition Phases

## Slide 4: Construction Deliverables
Construction Specialty Plans
  In Construction Transition Support (CTS) MBASE guidelines
Tracking and Control Deliverables
  Metrics
Working Deliverables
  Code base
  COTS packages (integrated, configuration)
  Revised Documentation

## Slide 5: Specialty Plans
Iteration Plan
Quality Management Plan
Test Plan
Inspection Plan
Security Plan (optional)
Safety Plan (optional)

## Slide 6: All Plans and Major Activities Should be Explicitly Planned
Allocate effort and people in LCP to
  Write plans
  Execute plan activities
  Prepare for RLCA and TRR reviews, core capability demos
Anticipate and account for risks
  Allocate extra time for risky items
  Explicitly schedule critical contingency plans
Be consistent with the class schedule

## Slide 7: Construction Planning Activities, Milestones and Deliverables

## Slide 8: Iteration Activities, Milestones and Deliverables

## Slide 9: Working Deliverables (per iteration)
Iteration Plan
Test Reports
Inspection Reports
Release Notes
Iteration Assessment Report
Source Code (under CM)
As-built OCD, SSRD, SSAD, FRD, LCP

## Slide 10: Iteration Plan
Plan for the upcoming iteration is planned in the current iteration
One iteration plan is input to the next iteration plan.
  Iteration Content
    Use Cases/Requirements Addressed
  Objectives
  Schedule of Activities
  Team Responsibilities
  ...

## Slide 11: Iteration Assessment Report
Each iteration is concluded by an iteration assessment
  Objectives Reached
  Adherence to Plan
  Use Cases/Requirements Implemented
  Results Relative to Evaluation Criteria
  External Changes Occurred
  Rework Required
  …

## Slide 12: Release Notes
The purpose of the Release Notes is to describe the release
  New Features and Important Changes since the previous release
  Upcoming Changes that will be incorporated in future releases
  Known Bugs and Limitations
  ...

## Slide 13: Metrics
A metric quantifies a characteristic of a process or product.
  Metrics can be directly observable quantities or can be derived from one or more directly observable quantities.
  Examples of raw metrics include:
    number of source lines of code,
    number of documentation pages,
    number of staff-hours,
    number of tests,
    number of requirements
  Examples of derived metrics include:
    source lines of code per staff-hour,
    defects per thousand lines of code,
    cost performance index.

## Slide 14
Note that this chart is generic, and each project will substitute specific tasks (units, milestones, SLOCs, etc. ). Additionally, each project is expected to produce multiple progress charts for different types of tasks, different teams, etc.

## Slide 18: Topic 4: Project Approach
Metrics
  Monitoring and control
Risk management
  CS 577 Top-10 risks
    Project risk management
    Risk-driven product and process level of detail

## Slide 19: Outline
Risk Management Definitions and Principles
Risk Assessment and Control
  Relations to CS577a Projects
Recommended Implementation Approach
Conclusions

## Slide 20: “If You Don’t Actively Attack the Risks,

## Slide 21: The Risks Will Actively Attack You.”
-Tom Gilb

## Slide 22: Importance of Risk Management
Addresses Complex Software Systems
Focuses Projects on Critical Risk Items
Provides Techniques for Handling Risk Items
Reduces Software Costs by Reducing Rework
  Usually 40-50% of software costs

## Slide 23: Rework Costs Concentrated in a Few High-Risk Items

## Slide 24: If Risk Management is so important, why don’t people do it?
Unwillingness to admit risks exist
    Leaves impression that you don’t know exactly what you’re doing
    Leaves impression that your bosses, customers don’t know exactly what they’re doing
    “Success-orientation”
Tendency to postpone the hard parts
    Maybe they’ll go away
    Maybe they’ll get easier, once we do the easy parts
Costs money and time up front

## Slide 25: When do people do Risk Management?
After they’ve been burned in similar situation
    Pain-avoidance
    Convincing evidence of consequences
When everybody involved is convinced that risks exist, but that it’s still worth going forward
    Everyone is a winner  Realistic expectations
When they’ve learned how to do it well
    Techniques not well-known, but can be learned

## Slide 26: Defining Risk
“Risk”: Possibility of loss or injury
-Webster
Risk Exposure =
(Probability of unsatisfactory outcome) X
(Loss if unsatisfactory outcome)

## Slide 27: Components of “Satisfactory Outcome:” Stakeholder Win Condition Satisfaction
Customer, Developer: Budget, Schedule
User: Functionality, Performance, Reliability, Usability
Maintainer: Modifiability, Portability
Product Line Manager: Reusability
Many Counterexamples:
  Lee, “The Day the Phones Stopped,” 1991
  Gibbs, “Software’s Chronic Crisis,” 1994
  Neumann, “Computer Related Risks,” 1995

## Slide 28: A Typical Software Risk Situation
Software Controls Spaceborne Experiment
PROB (Software has critical error) = 0.4
Loss from Critical Error Occurring = $20M
If Do Independent V&V:
  PROB (Critical Error Remains) = 0.05
  Added Cost to Software Project = $1M
If No Independent V&V:
  PROB (Critical Error Remains) = 0.2
  Added Cost to Software Project = $0

## Slide 29: The Fundamental Risk Analysis Paradigm
DO IV&V
NO IV&V
FIND CE
p = 0.35
DON’T FIND CE
DON’T FIND CE
FIND CE
NO CE
p = 0.05
p = 0.6
p = 0.2
p = 0.2
NO CE
p = 0.6
LOSS = - $1M
-21M
-1M
0
-20
0
EV = -2
EV = -4

## Slide 30: Outline
Risk Management Definitions and Principles
Risk Assessment and Control
  Relations to CS577a Projects
Recommended Implementation Approach
Conclusions

## Slide 31: Risk Assessment Role in Each Life-Cycle Phase
Evaluate Alternatives W.R.T Objectives
ID Potential High-Risk Areas
    No Alternatives Satisfy Objectives
    Major Satisfaction Uncertainty
Analyze Risk Items
Prioritize Risk Items
Objectives
Cost
Schedule
Function
Operation
Support
Reuse
Alternatives
Physical Architecture
Logical Architecture
COTS Software
Reused Software
Special Software
Risk ID
Checklist,
Techniques
Models,
Analysis Aids
Risk
Management
Plan RMPn
Revised
Objectives
Subset of
Alternatives
Prioritized
Risk Items

## Slide 32: Software Risk Management
Checklists
Decision driver analysis
Assumption analysis
Decomposition
Performance models
Cost models
Network analysis
Decision analysis
Quality factor analysis
Risk exposure
Risk leverage
Compound risk reduction
Buying information
Risk avoidance
Risk transfer
Risk reduction
Risk element planning
Risk plan integration
Prototypes
Simulations
Benchmarks
Analyses
Staffing
Milestone tracking
Top-10 tracking
Risk reassessment
Corrective action
Risk
Resolution
Risk
Assessment
Risk
Control
Risk
Identification
Risk
Analysis
Risk
Prioritization
Risk mgmt
Planning
Risk
Management
Risk
Monitoring

## Slide 33: Risk Identification Techniques
Risk-item checklists
Decision driver analysis
  Comparison with experience
  Win-lose, lose-lose situations
Decomposition
  Pareto 80 – 20 phenomena
  Task dependencies
  Murphy’s law
  Uncertainty areas

## Slide 34: Top 10 Risk Items: 1989 and 1995
Personal shortfalls
Schedules and budgets
Wrong software functions
Wrong user interface
Gold plating
Requirements changes
Externally-furnished components
Externally-performed tasks
Real-time performance
Straining computer science
Personnel shortfalls
Schedules, budgets, process
COTS, external components
Requirements mismatch
User interface mismatch
Architecture, performance, quality
Requirements changes
Legacy software
Externally-performed tasks
Straining computer science
1989
1995

## Slide 35: Example Risk-item Checklist: Staffing
Will you project really get all the best people?
Are there critical skills for which nobody is identified?
Are there pressures to staff with available warm bodies?
Are there pressures to overstaff in the early phases?
Are the key project people compatible?
Do they have realistic expectations about their project job?
Do their strengths match their assignment?
Are they committed full-time?
Are their task prerequisites (training, clearances, etc.) Satisfied?

## Slide 36: Candidate CS577 Risk Items
Personnel: commitment; compatibility; ease of communication; skills (management, Web/Java, Perl, CGI, data compression, …)
Schedule: project scope; IOC content; critical-path items (COTS, platforms, reviews, …)
COTS: see next charts; multi-COTS
Rqts, UI: mismatch to Library user needs
Performance: #bits; #bits/sec; overhead sources

## Slide 37: COTS and External Component Risks
COTS risks: immaturity; inexperience; COTS incompatibility with application, platform, other COTS; controllability
Non-commercial off-the shelf components: reuse libraries, government, universities, etc.
  Qualification testing; benchmarking; inspections; reference checking; compatibility analysis

## Slide 38: Advantages of COTS and Custom Software
COTS Integration
Predictable license costs
Broadly used, mature technology
Available now
Dedicated support organization
Hardware/software independence
Rich in functionality
Frequent upgrades
Custom Development
Complete freedom
Smaller, often simpler
Often better performance
Control of development/ enhancement
Control of reliability tradeoffs

## Slide 39: Disadvantages of COTS and Custom Software
COTS Integration
Up front license fees
Recurring maintenance fees
Dependency on vendor
Efficiency sacrifices
Functionality constraints
Integration not always trivial
No control over upgrades/ maintenance
Unnecessary features consume extra resources
Reliability often unknown/ inadequate
Scale difficult to change
Incompatibilities among vendors
Licensing and intellectual property issues
Custom Development
Development expensive/unpredictable
Availability date unpredictable
Maintenance expensive
Portability often expensive
Drains expert resources

## Slide 40: The Top Ten Software Risk Items
Risk Item
Risk Management Techniques
1. Personnel Shortfalls
Staffing with top talent; key personnel
agreements; incentives; team-building; training;
tailoring process to skill mix; peer reviews
2. Unrealistic schedules
and budgets
4. Requirements mismatch;
gold plating
5. User interface mismatch
Business case analysis; design to cost; incremental
development; software reuse; requirements descoping;
adding more budget and schedule
Stakeholder win-win negotiation; business case
analysis; mission analysis; ops-concept formulation;
user surveys; prototyping; early users’ manual;
design/develop to cost
Prototyping; scenarios; user characterization
(functionality, style, workload)
3. COTS; external components
Qualification testing; benchmarking; prototyping; reference checking; compatibility analysis; vendor analysis; evolution support analysis

## Slide 41: The Top Ten Software Risk Items (Concluded)
7. Requirements changes
9. Externally-performed
tasks
6. Architecture, performance,
quality
10. Straining Computer
Science capabilities
High change threshold; information
hiding; incremental development (defer
changes to later increments)
Reference checking; pre-award audits;
award-fee contracts; competitive design
or prototyping; team-building
Architecture tradeoff analysis and review boards;
simulation; benchmarking; modeling; prototyping;
instrumentation; tuning
Technical analysis; cost-benefit analysis;
prototyping; reference checking
8. Legacy software
Design recovery; phaseout options analysis;
wrappers/mediators; restructuring

## Slide 42
Risk Prioritization
Risk exposure
Risk leverage
  Betting analogy
  Adjective calibration
  Delphi/group techniques
  Compound risk reduction
Prioritization examples

## Slide 43
Risk Probability Assessment
Calculate probabilities, utilities
  Hard to do in general
Betting analogy
  Define “satisfactory” level
  Establish a personally meaningful amount of money, say, $100
  Determine how much money you would be willing to risk in betting on satisfactory outcome

## Slide 44
Risk Probability Assessment: Example
Establish proposition
  Using java will not cause us to slip our schedule
Establish betting odds
  No schedule slip: you win $100
  Schedule slip: you lose $500
Determine willingness to bet
  Willing: low risk
  Unwilling: high risk
  Not sure:
  risk due to uncertainty buy information

## Slide 46
Watch Out For Compound Risks
Pushing technology on more than one front
Pushing technology with key staff shortages
Vague user requirements with ambitious schedule
Untried hardware with ambitious schedule
Unstable interfaces with untried subcontractor
Reduce to non-compound risks if possible
Otherwise, devote extra attention to
  compound- risk containment

## Slide 47
Risk Management (RM)
Planning Process
Prioritized
Risk items
Candidate
RM techniques
Choose best cost-benefit mix of RM activities
Develop individual RM plans for each risk item
Coordinate RM plans with each other,project plan
Risk leverage
Analyses
Draft
RM plann
Revised
RM plann
Draft
RM plann+1

## Slide 48: Prioritizing Risks: Risk Exposure Risk Exposure - (Probability) (Loss of Utility)
Risk Probability
High
Low
Check
Utility -
Loss Estimate
Little
Risk
Low
Loss of Utility
High
Check
Probability
Estimate
Major
Risk

## Slide 49: Risk Exposure Factors (Satellite Experiment Software)
Unsatisfactory Outcome (UO)
Prob (UO)
Loss (UO)
Risk Exposure
A. S/ W error kills experiment
B. S/ W error loses key data
C. Fault tolerance features cause unacceptable
performance
D. Monitoring software reports unsafe condition
as safe
E. Monitoring software reports safe condition
as unsafe
F. Hardware delay causes schedule overrun
G. Data reduction software errors cause extra
work
H. Poor user interface causes inefficient
operation
I. Processor memory insufficient
J. DBMS software loses derived data
3 - 5
3 - 5
4 - 8
5
5
6
8
6
1
2
10
8
7
9
3
4
1
5
7
2
30 - 50
24 - 40
28 - 56
45
15
24
8
30
7
4

## Slide 50: Risk Exposure Factors and Contours: Satellite Experiment Software

## Slide 51: Risk Reduction Leverage (RRL)
RRL -
RE
BEFORE -
RE
AFTER
RISK REDUCTION COST
Spacecraft Example
LOSS (UO)
PROB (UO)
RE
B
B
LONG DURATION
TEST
$20M
0.2
$4M
FAILURE MODE
TESTS
$20M
0.2
$4M
PROB (UO)
RE
A
A
0.05
$1M
0.07
$1.4M
COST
$2M
$0.26M
RRL
4-1
2
= 1.5
4- 1.4
0.26
= 10

## Slide 52: Software Risk Management

## Slide 53: Risk Management Plans
For Each Risk Item, Answer the Following Questions:
1. Why?
Risk Item Importance, Relation to Project Objectives
2. What, When?
Risk Resolution Deliverables, Milestones, Activity Nets
3. Who, Where?
Responsibilities, Organization
4. How?
Approach (Prototypes, Surveys, Models, …)
5. How Much?
Resources (Budget, Schedule, Key Personnel)

## Slide 54: Risk Management Plan: Fault Tolerance Prototyping
1. Objectives (The “Why”)
  Determine, reduce level of risk of the software fault tolerance features causing unacceptable performance
  Create a description of and a development plan for a set of low-risk fault tolerance features
2. Deliverables and Milestones (The “What” and “When”)
  By week 3
    1. Evaluation of fault tolerance option
    2. Assessment of reusable components
    3. Draft workload characterization
    4. Evaluation plan for prototype exercise
    5. Description of prototype
  By week 7
    6. Operational prototype with key fault tolerance features
    7. Workload simulation
    8. Instrumentation and data reduction capabilities
    9. Draft Description, plan for fault tolerance features
  By week 10
    10. Evaluation and iteration of prototype
    11. Revised description, plan for fault tolerance features

## Slide 55: Risk Management Plan: Fault Tolerance Prototyping (concluded)
Responsibilities (The “Who” and “Where”)
  System Engineer: G. Smith
    Tasks 1, 3, 4, 9, 11, support of tasks 5, 10
  Lead Programmer: C. Lee
    Tasks 5, 6, 7, 10 support of tasks 1, 3
  Programmer: J. Wilson
    Tasks 2, 8, support of tasks 5, 6, 7, 10
Approach (The “How”)
  Design-to-Schedule prototyping effort
  Driven by hypotheses about fault tolerance-performance effects
  Use real-time OS, add prototype fault tolerance features
  Evaluate performance with respect to representative workload
  Refine Prototype based on results observed
Resources (The “How Much”)
  $60K - Full-time system engineer, lead programmer, programmer (10 weeks)*(3 staff)*($2K/staff-week)
  $0K - 3 Dedicated workstations (from project pool)
  $0K - 2 Target processors (from project pool)
  $0K - 1 Test co-processor (from project pool)
  $10K - Contingencies
  $70K - Total

## Slide 56: Risk Monitoring
Milestone Tracking
  Monitoring of risk Management Plan Milestones
Top-10 Risk Item Tracking
  Identify Top-10 risk items
  Highlight these in monthly project reviews
  Focus on new entries, slow-progress items
  Focus review on manger-priority items
Risk Reassessment
Corrective Action

## Slide 57: Project Top 10 Risk Item List: Satellite Experiment Software
Risk Item
Mo. Ranking
This Last #Mo.
Risk Resolution Progress
Replacing Sensor-Control Software 1 4 2 Top Replacement Candidate Unavailable
Developer
Target Hardware Delivery Delays 2 5 2 Procurement Procedural Delays
Sensor Data Formats Undefined 3 3 3 Action Items to Software, Sensor Teams;
Due Next Month
Staffing of Design V&V Team 4 2 3 Key Reviewers Committed; Need Fault-
Tolerance Reviewer
Software Fault-Tolerance May 5 1 3 Fault Tolerance Prototype Successful
Compromise Performance
Accommodate Changes in Data 6 - 1 Meeting Scheduled With Data Bus
Bus Design Designers
Testbed Interface Definitions 7 8 3 Some Delays in Action Items; Review
Meeting Scheduled
User Interface Uncertainties 8 6 3 User Interface Prototype Successful
TBDs In Experiment Operational - 7 3 TBDs Resolved
Concept
Uncertainties In Reusable - 9 3 Required Design Changes Small,
Monitoring Software Successfully Made

## Slide 58: Example Top-N Risk Item List

## Slide 59: Recommended Implementation Approach Incremental Evolution
1. Establish top-10 risk item tracking process
  Simple; inexpensive; gets early results
2a. Experimentally apply selected risk mgmt. Techniques
  SEI Risk Taxonomy; risk assessment tools
2b. Develop, apply risk mgmt. Plan on initial project
3a. Extend risk assessment and control to all projects
3b. Experimentally apply advanced risk mgmt.
4. Evolve the mapping of best risk management techniques to your project situations

## Slide 60: Conclusions
Risk Management is a good match for complex software projects
  Avoiding software surprises, show-stoppers
  Reducing costs
Proven risk management techniques are available
Risk management is not a cookbook approach

## Slide 61
4. Approach (How?)
4.1 Monitoring and Control
  4.1.1 Closed loop feedback control
  4.1.2 Reviews
  4.1.3 Status Reporting
  4.1.4 Risk Monitoring and Control
4.2 Methods, Tools, and Facilities
4.3 Configuration Management
4.4 Quality Assurance

## Slide 62: 4.1 Risk Management
Identify major sources of risk in the software development project, and show how the project will address, monitor, and resolve these sources of risk.
System Priorities (FRD 3.1) identified optional requirements that can be left out in the case of schedule slippage

## Slide 63: 4.1 Risk Management (continued)
For every critical risk, you can indicate:
  Description
  Potential Damage to schedule and stakeholders
  Actions to Mitigate Risk
  Contingency Plan
  Change in Status
Different point of view from FRD
  Risk assessment and feasibility of mitigation approach
  (later in FRD) Risk Exposure = (Probability of unsatisfactory outcome) x (Loss if unsatisfactory outcome)

## Slide 64: Example Risk Management
4.1.1 Personnel
Description: Team member departure.
Potential Effects: Team resources will be stretched due to a lack of personnel. As result the project could fall behind schedule.
Avoidance or Containment Plan: To avoid this desperate situation it is the job of the project leader to maintain and monitor team felicity. If team member happiness is low the potential for desertion will be high. Thus is becomes vital for the project manager to ensure the morale of all the members of his team. Similar to ‘hand-holding’ of the customer, the project lead must do the same with his staff members. A manager must have the ability of discernment to identify the problem and the patience to mend the problem.
From Team 4’s LCA
From Team 12’s LCA

## Slide 65
4.4 Quality Assurance Functions
Documentation and Code Standards
Standards Compliance Monitoring
Plans & Policies Compliance Monitoring
Review & Test Monitoring
Corrective Action Monitoring
Verification and Validation
* QA is everyone’s job
  --but people need reminders

## Slide 66: 4.7 Status Monitoring and Control
Describe techniques, procedures, and reports to be used in tracking project progress vs. plans and expenditures vs. budgets. Include, as appropriate:
    Summary Task Planning Sheets;
    Earned Value Status Reports
    Project Expenditure Summaries;
    Cumulative Milestone Progress Reports;
    PERT/ COST Systems;
    Budget-Schedule-Milestone Charts;
    Personnel Loading Charts;
    Detailed Expenditure vs. Budget Reports.

## Slide 67: 4. Project Risk Assessment
Any combinations of capabilities or objectives whose feasibility is difficult to assure, are major sources of risk.
Risk Assessment consists of risk identification, risk analysis and risk prioritization.
  Organize major sources of risk into a Top-10 (or Top-N) risk items list to be monitored via LCP 4.1 (Risk Management and Monitoring Procedures)
  For critical risks indicate:
    Description
    Risk Exposure : magnitude and probability of loss
    Risk Reduction Leverage: in reducing risk exposure
    Actions to mitigate risk
    Contingency plan
  Identify low-priority requirements that can be left out in case of schedule slippage

## Slide 68: Software Risk Management Techniques

## Slide 69
Sample risk analysis from Team 16-1 Spring ’99 (only the first three risks are shown)