## Slide 1: Objectives For Topic 3
Selections of CS 577 MBASE software engineering economics
  Exemplify some of the specific economic oriented models taught and used within our SWE project course

## Slide 2: Topic 3: Selections of CS 577 MBASE software engineering economics
Shared Vision
  WinWin
  MBASE section 2 (DMR style results chains)
Requirements, Milestones, Lifecycles
  Expectations management
    Simplifiers and complicators
  Lifecycle process models
    Schedule as an independent variable (SAIV) and fixed schedules
  Cost estimation
    Student COCOMO II
Scheduling
  MS Project
Business case analysis
  System life cycle costs and benefits
  Return on investment

## Slide 3: Win Win

## Slide 4: The Challenge: Avoiding Requirements Mismatches

## Slide 5: Why Software Projects Fail

## Slide 6: WinWin
Success-critical stakeholders negotiate and prioritize the requirements for a software development project

## Slide 7: Who Are The Stakeholders?
Customers
Users
Programmers
Architects
Domain Experts
Analysts
Marketing
Sales
Management
…?

## Slide 8: WinWin Definition
The win-win approach is a set of principles, practices, and tools, which enable a set of interdependent stakeholders to work out a mutually satisfactory (win-win) set of shared commitments.

## Slide 9: Win-lose Generally Becomes Lose-lose
Actually, nobody wins in these situations

## Slide 10: Key Concepts
Win Condition: objective which makes a stakeholder feel like a winner
Issue: conflict or constraint on a win condition
Option: A way of overcoming an issue
Agreement: mutual commitment to an option or win condition

## Slide 11: WinWin Negotiation Model
Win Condition
Agreement
Option
Issue
involves
addresses
adopts
covers
WinWin Equilibrium State - All Win Conditions covered by Agreements - No outstanding Issues

## Slide 12: WinWin Critical Success Factors
Appropriate staffing of stakeholder representatives, facilitator function
  Stakeholder representatives: empowered, committed, representative, collaborative, knowledgeable
  Facilitators: some understanding of stakeholder domains, collaboration management ability
  Good facilitators can be participants also
Beginning of shared vision

## Slide 13
Spiral Model Refinements
Where do objectives, constraints, alternatives come from?
  Win Win extensions
Lack of intermediate milestones
  Anchor Points: LCO, LCA, IOC
  Concurrent-engineering spirals between anchor points
Need to avoid model clashes, provide more specific guidance
  MBASE
Evaluate product and
The
WinWin
Spiral Model
2. Identify Stakeholders’
win conditions
1. Identify next-level
Stakeholders
Reconcile win
conditions. Establish
next level objectives,
3.
process alternatives.
Resolve Risks
4.
Define next level of product and
process - including partitions
5.
Validate product
and process
definitions
6.
Review, commitment
7.
Win-Win
Extensions
Original
Spiral
constraints, alternatives

## Slide 14: Why Use WinWin ?
The alternatives don’t work
  Win-lose often leads to lose-lose
Avoids costly rework
  100X cost to fix requirements after delivery
Builds trust and manages expectations
  Looking out for other’s needs builds trust
  Balancing needs leads to realistic expectations
Helps stakeholders adapt to change
  Shared vision and the flexibility of quick re-negotiation
Helps to build institutional memory
  Capture the why behind the what, the argument behind the artifact

## Slide 15: Why Use EasyWinWin OnLine?
Speed and efficiency for modest system, distributed stakeholders
  Email and telephone: 1-3 months
  Early WinWin toolset: 1-3 weeks
  EasyWinWin OnLine: 2-5 days
Low entry barrier for stakeholders
  Easy to learn and use
  Intuitive, time-efficient process

## Slide 16: Steps of EasyWinWin OnLine
1. Review and expand negotiation topics
2. Brainstorm stakeholder interests
3. Converge on Win Conditions
4. Capture a glossary of Terms
5. Prioritize Win Conditions
6. Identify Issues and Options
7. Negotiate Agreements
8. Organize negotiation results
Notes: This slide gives an overview about the EasyWinWin activities and shows which thinkLets/tools are adopted in the approach

## Slide 17: Easy WinWin Tool Support

## Slide 18: MBASE Section 2
Shared Vision

## Slide 19: MBASE OCD Section 2: Shared Vision
2. Shared Vision
2.1 System Capability Description
2.1.1 Benefits Realized
2.1.2 Results Chain
2.2 Key Stakeholders
    Roles, responsibilities, contributions to Results Chain
2.3 System Boundary and Environment
  Context Diagram
2.4 Major Project Constraints
  Add for Scaling Up:
    2.5 Top-level business case
    2.6 Inception phase plan, resources required
    2.7 Initial Spiral objectives, constraints, alternatives, risks

## Slide 20: System Capability Description
Concise description of why system should be built
  For (target customer)
  Who (statement of the need or opportunity)
  The (product name) is a (product category)
  That (statement of key benefit-that is, compelling reason to buy)
  Unlike (primary competitive alternative)
  Our product (statement of primary differentiation)
Should be able to pass “elevator test”
  Convince executive while riding up/down elevator

## Slide 21: The Information Paradox (Thorp)
No correlation between companies’ IT investments and their market performance
Field of Dreams
  Build the (field; software)
  and the great (players; benefits) will come
Need to integrate software and systems initiatives

## Slide 22: DMR/BRA Results Chain
INITIATIVE
OUTCOME
OUTCOME
Implement a new order
entry system
ASSUMPTION
Contribution
Contribution
Order to delivery time is
an important buying criterion
Reduce time to process order
Reduced order processing cycle
(intermediate outcome)
Increased sales
Reduce time to deliver product

## Slide 23
Critical Success Factors for Adoption

## Slide 24: Results Chain: Hispanic Digital Archive (HDA)
Major donor
funding
Viable
HDA
Archive
Digitize HDA
Archive
Viable
IBM DL
package
HDA PR, training
for USC, community
Develop
HDA Software
Assumption
Outcome
Initiative
Contribution
Staff, train
HDA
Ops/Maint
personnel
Viable
HDA
System
Digital
HDA assets
Sustainable
HDA Archive
World-class
Hispanic
research,
education,
outreach
support

## Slide 25: Example: Team 17 (Web Mail) OCD 2.1.2 Results Chain
Design and implement a Web mail system
Communication services are vital to quality academic life.
Make email services easier to access and use.
Creation of infrastructure for future Web-based services.
Improve academic life at USC.
Design and implement more advanced Web-based tools.
Make graphical email available from any computer with web access.
Create web-based basis for communication infrastructure.
Create other systems integrated with Web mail system.
Allow better communication between students, faculty, and staff.
Provide better access to academic information and services.
INITIATIVES
CONTRIBUTIONS
OUTCOMES
ASSUMPTION

## Slide 26: Key Stakeholders
Frequently users, Customers, Developers, Maintainers
Sometimes Interfacers, Subcontractors, Supplier’s,
Venture Capitalists, Testers, General Public
Identify each stakeholder by
  Home organization
  Authorized project representative
  Relation to Results Chair

## Slide 27: Example: Team 3 (Pathology image search engine) OCD 2.3 System Boundary and Environment
Users
1. Search of Pathology slides
2. Addition and removal of web sites from search list
3. UMLS integration
4. On-line help
Administrator
MedWeb Web system
Digitized slides and images from USC as well as other schools
Developers
Client

## Slide 28: Topic 3: Selections of CS 577 MBASE software engineering economics
Shared Vision
  WinWin
  MBASE section 2 (DMR style results chains)
Requirements, Milestones, Lifecycles
  Expectations management
    Simplifiers and complicators
  Lifecycle process models
    Schedule as an independent variable (SAIV) and fixed schedules
  Cost estimation
    Student COCOMO II
Scheduling
  MS Project
Business case analysis
  System life cycle costs and benefits
  Return on investment

## Slide 29: Requirements Expectations Management
Simplifiers and complicators

## Slide 30: Unmet Expectations Problems
LCO success condition
  Describes at least one feasible architecture
  Satisfying requirements within cost/schedule/resource constraints
  Viable cost-effective business case
  Stakeholder concurrence on key system parameters
Projects That Failed LCO Criteria
1996: 4 out of 16 (25%)
1997: 4 out of 15 (27%)
why?

## Slide 31
Requirements and Expectations: Domain Model Clashes
Easy/hard things for software people
  “If you can do queries with all those and’s, or’s, synonyms, data ranges, etc., it should be easy to do natural language queries.”
  “If you can scan the document and digitize the text, it should be easy to digitize the figures too.”
Easy/hard things for librarians
  “It was nice that you could add this access feature, but it overly (centralizes, decentralizes) control of our intellectual property rights.”
  “It was nice that you could extend the system to serve the medical people, but they haven’t agreed to live with our usage guidelines.”

## Slide 32: 1998 Simplifier/Complicator Experiment
Identify application’s general simplifiers and complicators
  For applications particular sub-domain
  For both developers and clients
Provide refinements with explanations to developers and clients
  Highlight relation to risk management activities
Homework exercise to analyze simplifiers and complicators
  Practice on two upcoming projects
Evaluate effect on LCO review success rate

## Slide 33
Example S&C’s
1, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 20, 31, 32, 35, 36, 37, 39
Type of
Application
Simple Block Diagram
Examples
Simplifiers
Complicators
Multimedia
Archive

Use standard
query languages

Use standard or
COTS search
engine

Uniform media
formats

Natural language
processing

Automated
cataloging or
indexing

Digitizing large
archives

Digitizing
complex or fragile
artifacts

Automated
annotation/descrip
tion/ or meanings
to digital assets

Integration of
legacy systems
MM asset
info
Catalog
MM
Archive
query
MM asset
update
query
update
notification

Rapid access to
large Archives

Access to
heterogeneous
media collections

## Slide 34
Specialized S&C’s

## Slide 35
Simplifiers | Risks and Trade-offs
Generic Uniform Media Formats Specific All video clips are stored using an open file format for video/audio (e.g., MPEG). All film stills are stored using an open image file format (e.g., JPEG). The inverse complicator is to store film clips using streaming video technologies | This means that we may have to convert existing digital assets or digitize the original media, which may be costly. A unique file format limits the user base to those who have viewers for that particular file format The chosen file format may not be the most efficient for the various types of media (in terms of compression rates, quality, etc...)
Generic Use Standard Query Languages Specific Organize catalog and archive relationally so that queries will be limited to standard search formats,: match exactly by value on any of the fields with or without using boolean combinations (AND, OR, NOT, etc...), or using pattern matching (SQL LIKE keyword) | May not be as effective for "discovering" assets in the archive: users must know what they're looking for, in order to search for it
Generic Use Standard COTS Specific Use a standard Relational Database Management System (RDBMS) that supports storing multi-media assets | A Relational Database Management System may not be most suited for archival of multi-media assets. A Relational Database Management System may have a high initial cost, high implementation, and high administration cost (requires specialized knowledge skills)

## Slide 36
Complicators | Risks and Trade-offs
Generic Natural Language Processing Specific Store the information only in one language (e.g., English) and provide dynamic translation into Chinese, Japanese and Korean The inverse simplifier is to store the same information in 4 different languages (English, Chinese, Japanese and Korean). | The first approach is a complex, error-prone, expensive natural language processing issue The second approach will require more storage space, in addition to acquiring the translations
Generic Digitizing Large Archives Specific Digitizing film clips from the entire collection of films (which grows at a very fast rate of 800 films per year for Indian films alone) | If each film clip requires around 10 MB, then the rate of growth of the database will be of 8GB a year (exclusive of catalog information)
Generic Integration of "Legacy" Systems Specific Do not require Real-Video plug-in for Web browsers to allow users to view streamed film clips | We cannot use more effective multi-media formats, which are becoming standard technologies

## Slide 37: The Results
Projects That Failed LCO Criteria
1996: 4 out of 16 (25%)
1997: 4 out of 15 (27%)
1998: 1 out of 20 (5%)
1999: 1 out of 22 (4%)
40% of Student critiques cited S&C’s as helpful (and more since)
  In focusing on achievable requirements set within tight schedule
  In understanding project risks and tradeoffs

## Slide 38: Lifecycle process models
Schedule as an independent variable (SAIV) and fixed schedules

## Slide 39: Is There A Problem?
The clients want this system on a ridiculously short (fixed) schedule
And they aren’t even willing to commit on just exactly what they want

## Slide 40
Is There A Problem?
The clients want this system on a ridiculously short (fixed) schedule
And they aren’t even willing to commit on just exactly what they want
  Usually, it leads to a Death March

## Slide 41
Is There A Problem?
The clients want this system on a ridiculously short (fixed) schedule
And they aren’t even willing to commit on just exactly what they want
Usually, it leads to a Death March, but...
Usually, it’s an opportunity to succeed via the SAIV process model
  Schedule As Independent Variable

## Slide 42
Schedule as Independent Variable
“If schedule is your independent variable, then just modulate your functionality to meet schedule.”
Critical success factors:
  Prioritized requirements
  A conservative schedule estimate
  Software architecting for ease of change
  Schedule tracking for midcourse corrections
Detailed approach below
University of Southern California
Center for Software
Engineering
C
S
E
USC

## Slide 43
Success Models Drive Other Model Choices
Success Model
Key Stake-holders
Key Property Models
Process Model
Product Model
Demo agent-based E-commerce system at COMDEX in 9 months
Entrepreneurs, venture capitalists, customers
Schedule estimation
Schedule-As-Independent Variable (SAIV)
Domain constrained by schedule; architected for ease in dropping features to meet schedule
Safe air traffic control system
Controllers, Govt. agencies, developers
Safety models
Initial spiral to risk-manage COTS, etc.; Final waterfall to verify safety provisions
Architected for fault tolerance, ease of safety verification

## Slide 44
Stakeholders
Domain
models
Success
models
Negotiate
mutually
satisfactory
entry and
exit
conditions
Product
models
Set
context
for
Property
models
Provide
measures
for
Constrain
Process
models
Guide
development
of
Describe
enterprise
context in
Constrain
Serve and satisfy
Provide
parameters
for
Provide
parameters
for
Product
evaluation
criteria
Process
entry/exit
criteria
Planning and control
Milestone content
Evaluation and
analysis
Success
Models
Product
Models
Process
Models
Property
Models
MBASE Model Integration Framework
1
. Identify
next level
stakeholders
7
. Review,
commit
6. Validate
product
and process
definitions
5. Define next level of
product and process
4. Evaluate
product
and process
alternatives
2. Identify stakeholders
win conditions
3. Reconcile
win
conditions,
establish
objectives,
constraints,
and
alternatives
LCO
LCA
IOC
MBASE Spiral
Behavioral Integration
Element Integration

## Slide 45: The SAIV Process Model
1. Shared vision and expectations management
2. Feature prioritization
3. Schedule range estimation
4. Architecture and core capabilities determination (flexibility needs assessment)
5. Incremental development
6. Change and progress monitoring and control

## Slide 46: Shared Vision, Expectations Management, and Feature Prioritization
Use stakeholder win-win approach
Developer win condition: Don’t overrun fixed 9-month schedule
Clients’ win conditions: 24 months’ worth of features
Win-Win negotiation
  Which features are most critical?
  COCOMO II: How many features can be built within a 9-month schedule?

## Slide 47: COCOMO II Estimate Ranges

## Slide 48: Software Product Production Function
Value of software product to organization
Investment
High-payoff
Diminishing returns
Operating
system
Data management
Basic application functions
Main application functions
Humanized I/O
Secondary application functions
Animated graphics
Tertiary Application Functions
Natural speech input
T=12 mo.
T=6 mo.
Availability of
delivery by time T
90%
90%
50%
50%
COCOMO II estimate

## Slide 49: Core Capability Incremental Development, and Coping with Rapid Change
Core capability not just top-priority features
  Useful end-to-end capability
  Architected for ease of adding, dropping marginal features
Worst case: Deliver core capability in 9 months, with some extra effort
Most likely case: Finish core capability in 6-7 months
  Add next-priority features
Cope with change by monitoring progress
  Renegotiate plans as appropriate

## Slide 50: SAIV Experience I: USC Digital Library Projects
Life Cycle Architecture package in fixed 12 weeks
  Compatible operational concept, prototypes, requirements, architecture, plans, feasibility rationale
Initial Operational Capability in 12 weeks
  Including 2-week cold-turkey transition
Successful on 17 of 19 projects
  Failure 1: too-ambitious core capability
    Cover 3 image repositories at once
  Failure 2: team disbanded
    Graduation, summer job pressures

## Slide 51: Rapid ValueTM Project Approach
Define
Design
Develop
Deploy
Lines of readiness
Are we ready for the next step?
Iteration
Scope, Listening, Delivery focus
Identify System Actors
Document Business Processes
Generate Use Cases
Define basic development strategies
Object Domain Modeling
Detailed Object Design, Logical Data Model
Object Interactions, System Services
Polish Design, Build Plan
Build 1
Build 2
Stabilization Build
Release to Test
Beta Program
Pilot Program
Production
16-24 week fixed schedule
LA SPIN
Copyright © 2001 C-bridge

## Slide 52: Conclusions: SAIV Critical Success Factors
Working with stakeholders in advance to achieve a shared product vision and realistic expectations;
Getting clients to develop and maintain prioritized requirements;
Scoping the core capability to fit within the high-payoff segment of the application’s production function for the given schedule;
Architecting the system for ease of adding and dropping features;
Disciplined progress monitoring and corrective action to counter schedule threats
Also works for Cost as Independent Variable
  And “Cost, Schedule, Quality: Pick All Three”

## Slide 53: Cost estimation
Student COCOMO II

## Slide 54: Purpose of COCOMO II
To help people reason about the
cost and schedule implications of
their software decisions

## Slide 55: Major Decision Situations Helped by COCOMO II
Software investment decisions
  When to develop, reuse, or purchase
  What legacy software to modify or phase out
Setting project budgets and schedules
Negotiating cost/schedule/performance tradeoffs
Making software risk management decisions
Making software improvement decisions
  Reuse, tools, process maturity, outsourcing

## Slide 56: COCOMO II PM Estimates and CS 577 Rough Team Size (for risk assessment, not precise planning)
1 CS 577 Team Member ~ = 2 COCOMO II Person Months
(“EST-Most Likely” from display)
1 CS 577 TM ~ = (12 weeks)(12 project hours/week) ~ = 144 proj-hr
2 COCOMO II PM ~ = (2)(152 hr/PM)(.66project hr/total hr)*(.72 in CS 577)** ~ = 144 proj-hr
* .66 of day spent doing project work (see Figure)
** 72% of effort in Elaboration and Construction stage

## Slide 58
COCOMO II Model Stages

## Slide 59
Relations to MBASE*/Rational Anchor Point Milestones
App. Compos.
Inception
Elaboration, Construction
LCO, LCA
IOC
Waterfall Rqts.
Prod. Des.
LCA
Development
LCO
Sys Devel
IOC
Transition
SRR
PDR
Construction
SAT
Trans.
*MBASE: Model-Based (System) Architecting and Software Engineering
Inception Phase
Elaboration

## Slide 60
Early Design and Post-Architecture Model




Factors
Scale
Process
Size
Effort
s
Multiplier
Environment










Environment: Product, Platform, People, Project Factors
Size: Nonlinear reuse and volatility effects
Process: Constraint, Risk/Architecture, Team, Maturity Factors




Factors
Scale
Process


Effort
Schedule
Multiplier



## Slide 61
Relative
cost
Amount Modified
1.0
0.75
0.5
0.25
0.25
0.5
0.75
1.0
0.55
0.70
1.0
0.046
Usual Linear
Assumption
Data on 2954
NASA modules
[Selby, 1988]
Nonlinear Reuse Effects

## Slide 62
COCOMO II. 2000 Productivity Ranges
Productivity Range
1
1.2
1.4
1.6
1.8
2
2.2
2.4
Product Complexity (CPLX)
Analyst Capability (ACAP)
Programmer Capability (PCAP)
Time Constraint (TIME)
Personnel Continuity (PCON)
Required Software Reliability (RELY)
Documentation Match to Life Cycle Needs (DOCU)
Multi-Site Development (SITE)
Applications Experience (AEXP)
Platform Volatility (PVOL)
Use of Software Tools (TOOL)
Storage Constraint (STOR)
Process Maturity (PMAT)
Language and Tools Experience (LTEX)
Required Development Schedule (SCED)
Data Base Size (DATA)
Platform Experience (PEXP)
Architecture and Risk Resolution (RESL)
Precedentedness (PREC)
Develop for Reuse (RUSE)
Team Cohesion (TEAM)
Development Flexibility (FLEX)
Scale Factor Ranges: 10, 100, 1000 KSLOC

## Slide 63
COCOMO Model Comparisons
COCOMO
Ada COCOMO
COCOMO II:
Application Composition
COCOMO II:
Early Design
COCOMO II:
Post-Architecture
Size
Delivered Source Instructions
(DSI) or Source Lines of
Code (SLOC)
DSI or SLOC
Application Points
Function Points (FP) and
Language or SLOC
FP and Language or SLOC
Reuse
Equivalent SLOC = Linear

(DM,CM,IM)
Equivalent SLOC = Linear

(DM,CM,IM)
Implicit in Model
Equivalent SLOC = nonlinear

(AA, SU,UNFM,DM,CM,IM)
Equivalent SLOC = nonlinear

(AA, SU,UNFM,DM,CM,IM)
Rqts. Change
Requirements Volatility
rating: (RVOL)
RVOL rating
Implicit in Model
Change % : RQEV
Maintenance
Annual Change Traffic
(ACT) =
%added + %modified
ACT
Object Point ACT

(ACT,SU,UNFM)

(ACT,SU,UNFM)
Scale (b) in
MM
NOM
=a(Size)
b
Organic: 1.05 Semidetached:
1.12 Embedded: 1.20
Embedded: 1.04 -1.24
depending on degree of:

early risk elimination

solid architecture

stable requirements

Ada process maturity
1.0
.91-1.23 depending on the
degree of:

precedentedness

conformity

early architecture, risk
resolution

team cohesion

process maturity (SEI)
.91-1.23 depending on the
degree of:

precedentedness

conformity

early architecture, risk
resolution

team cohesion

process maturity (SEI)
Product Cost Drivers
RELY, DATA, CPLX
RELY
*
, DATA, CPLX
*
,
RUSE
None
RCPX
*

, RUSE
*

RELY, DATA, DOCU
*

,
CPLX

, RUSE
*

Platform Cost Drivers
TIME, STOR, VIRT, TURN
TIME, STOR, VMVH,
VMVT, TURN
None
Platform difficulty: PDIF
*

TIME, STOR, PVOL(=VIRT)
Personnel Cost
Drivers
ACAP, AEXP, PCAP,
VEXP, LEXP
ACAP
*
, AEXP, PCAP
*
,
VEXP, LEXP
*
None
Personnel capability and
experience: PERS
*

,
PREX
*

ACAP
*
, AEXP

, PCAP
*
,
PEXP
*

, LTEX
*

, PCON
*

Project Cost Drivers
MODP, TOOL, SCED
MODP
*
, TOOL
*
, SCED,
SECU
None
SCED, FCIL
*

TOOL
*

, SCED, SITE
*

* Different Multipliers

Different Rating Scale
RQEV

## Slide 64
Percentage of sample projects within 30% of actuals
-Without and with calibration to data source
COCOMO II Estimation Accuracy:
COCOMO81
COCOMOII.2000
COCOMOII.1997
# Projects
63
83
161
Effort
Schedule
81%
52%
64%
75%
80%
61%
62%
72%
81%
65%

## Slide 65: More Cost Models: Effort Model Selection Matrix
Stephen Jan 2000
“-” is any value

## Slide 66: Topic 3: Selections of CS 577 MBASE software engineering economics
Shared Vision
  WinWin
  MBASE section 2 (DMR style results chains)
Requirements, Milestones, Lifecycles
  Expectations management
    Simplifiers and complicators
  Lifecycle process models
    Schedule as an independent variable (SAIV) and fixed schedules
  Cost estimation
    Student COCOMO II
Scheduling
  MS Project
Business case analysis
  System life cycle costs and benefits
  Return on investment

## Slide 67: Objectives of Software Development
Deliver a computer program?
Deliver a correct computer program?
Deliver a correct, maintainable computer program?
Make winners of key stakeholders
  Operators: procedures, facility preparation
  Users, Operators, Maintainers: data conversion, training, transition procedures, support capabilities

## Slide 68: 2.1 Overall Life Cycle Strategy
Describe overall approach:
  Choice of process model(s) used and major life cycle stages, phases and milestones
  Nature and phasing of the planned prototypes
  Nature and phasing of the successive increments to be developed (if applicable)
  Top-level milestone charts and activity networks showing the sequence of major products and activities.

## Slide 69: Process model for CS 577
Engineering Stage
  Inception Phase (LCO)
    WinWin Spiral cycle for LCO
    LCO Architecture Review Board review
  Elaboration Phase (LCA)
    WinWin Spiral cycle
    LCA Architecture Review Board review
Production Stage
    WinWin Spiral Cycle
    Risk-driven Waterfall Cycle
    Transition Readiness Review

## Slide 71: Process model for CS 577 (continued)
Transition Phase
  Release Readiness Review
Support Stage (Customer responsibility)
  Release 1
  Release Readiness Review
  Release 2
  Release Readiness Review
  …

## Slide 72
Management Checkpoints
Inception
Elaboration
Construction
Transition
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Iteration 7
MAJOR
MILESTONES
Initial Operational capability milestone
Lifecycle Objectives Milestone
Lifestyle Architecture Milestone
Product Release Milestone
Strategic focus on global concerns of the entire software project
Minor Milestones
Tactical focus on local concerns of current iteration
Status Assessment
Periodic synchronization of stakeholder expectations

## Slide 73
Idea
Architecture
Beta releases
Products
Inception
Elaboration
Construction
Transition
Engineering Stage
Manufacturing Stage

## Slide 74
Workflow Balance over the Life Cycle
Inception
Elaboration
Construction
Transition
Management
Environment
Requirements
Design
Implementation
Testing
Deployment

## Slide 75: Process Model Decision Table
Objectives, Constraints
Alternatives
Model
Example
Growth Envelope
Understanding of Requirements
Robustness
Available Technology
Architecture Understanding
Limited
COTS
Buy COTS
Simple Inventory Control
Limited
4GL, Transform
Transform or Evolutionary Development
Small Business - DP Application
Limited
Low
Low
Low
Evolutionary Prototype
Advanced Pattern Recognition
Limited to Large
High
High
High
Waterfall
Rebuild of old system
Low
High
Risk Reduction followed by Waterfall
Complex Situation Assessment
High
Low
High-performance Avionics
Limited to Medium
Low
Low-Medium
High
Evolutionary Development
Data Exploitation
Limited to Large
Large Reusable Components
Medium to High
Capabilities-to-Requirements
Electronic Publishing
Very Large
High
Risk Reduction &Waterfall
Air Traffic Control
Medium to Large
Low
Medium
Partial COTS
Low to Medium
Spiral
Software Support Environment

## Slide 76
CS 577 Typical Software Process
RLCA
INITIAL
SUBMITTAL
IOC
WATERFALL-TYPE
LCO
SPIRAL CYCLE
SPIRAL CYCLE
CONSTRUCTION BEGINS
EARLY PROTOTYPE
TESTING BEGINS
LCA

## Slide 77: Example Overall Life Cycle Strategy
From Hispanic Digital Archive LCP:
The proposed amount of flexibility. Therefore, we propose to use the evolutionary development as our software engineering process as suggested by the Process Model Decision Table. Further, we propose to use the WinWin Spiral Model as it is understood fairly well by the team members and system envisages a moderately understood set of requirements to be met with a low degree of robustness but with a high is supported by the Center for Software Engineering, University of Southern California. The schedules for project activities have been estimated using COCOMO II post-architecture model.

## Slide 78: 2.2 Phase Milestones and Schedules
Provide more detailed milestone charts and activity networks
For each increment, indicate:
  Completion of integration, of product test, and of acceptance test
  Major dependencies on development activities, on other increments, on facilities, etc.;
  Milestones showing the overall order in which components are integrated, and the intermediate stages of increment and acceptance testing.
  How these are synchronized with milestones for preparation of test drivers, facilities, etc... for the various increments.

## Slide 79
Phases Milestones and Schedules
Measurable milestones
  - Not “Get team thinking about GUI”
  - But “Obtain team consensus & GUI”
Specific schedule dates
Gantt charts
    Calendar-oriented tasks lists
    Task dependencies optional
Activity networks/PERT charts
    - Task dependencies explicit

## Slide 80: Phase Deliverables and Completion Criteria
Describe for each Phase
  The Deliverable
  The Exit or Completion Criteria

## Slide 81
2.2.1 Inception Phase
During this phase initial understanding of the desired system must be accomplished. This is achieved by defining the scope of the project so all stakeholders are in concurrence. Feasibility analysis and prioritization of the tasks must also be done here.
2.2.2 Elaboration Phase
During this phase prototyping must demonstrate the architecture’s feasibility and stability. Risks and plans to minimize risk must also be assessed and developed in this phase. Additionally an appropriate development schedule should be created. Furthermore, cost estimates must also be conceived here. Moreover, an operational impact analysis must be completed to observe how useful the proposed would be to the customer and user.
Example Phase Deliverables and Completion Criteria

## Slide 82: Example Project Schedule
Figure . High Level PlagueWare Project Schedule

## Slide 83
Example Detailed Schedule

## Slide 84: Topic 3: Selections of CS 577 MBASE software engineering economics
Shared Vision
  WinWin
  MBASE section 2 (DMR style results chains)
Requirements, Milestones, Lifecycles
  Expectations management
    Simplifiers and complicators
  Lifecycle process models
    Schedule as an independent variable (SAIV) and fixed schedules
  Cost estimation
    Student COCOMO II
Scheduling
  MS Project
Business case analysis
  System life cycle costs and benefits
  Return on investment

## Slide 85: Feasibility Rationale Guidelines (FRD)

## Slide 86: Content
Business Case Analysis
  Satisfactory (Win-Win) return on investment
Consistency and Feasibility Rationale
  If we build to this architecture,
  We will support the operational concept,
  Be consistent with the prototypes,
  Satisfy the requirements,
  And stay within the budgets and schedules in the plan

## Slide 87: Audience and Participants
Primary audience: ARB members
  Key system stakeholders
  Experienced peers
  Technical Specialists in critical areas
Also valuable to stakeholders outside ARB
Project manager responsible for content
  OCD author should prepare business case
  All stakeholders responsible for consistency and feasibility via Win-Win negotiations
  Agreements can be contingent on demonstration of feasibility

## Slide 88: 2. Product Rationale
Rationale for the product being able to satisfy the system specifications and stakeholders (e.g. customer, user).
Should be consistent with:
  Development costs (from LCP)
  SSRD and SSAD for Requirements satisfaction

## Slide 89: 2.1 Business Case Analysis
Describe the impact of the product in mainly monetary terms.
  How much does it cost to develop and to operate?
  How much added value does it generate?
  How high is its return on investment?
Non-monetary factors may be also decisive. For instance, “added value” can include the improved quality of the service provided by the product.

## Slide 90: 2.1.1 Development Cost Analysis
Provide a summary of the full development cost, including hardware, software, people, and facilities costs.
Proof that schedule is enough to deliver required capability
Should be consistent with Budgets in LCP

## Slide 91: 2.1.2 Transition Cost Estimate
Rough estimate of costs which accumulate during transition of the product into production use (e.g. training)
Operational and support software
  Data preparation, COTS licenses
  Operational readiness testing
Site preparation
  Facilities, equipment, supplies

## Slide 92: Transition Costs Estimate Example
From Hispanic Digital Archive’s LCA

## Slide 93: 2.1.3 Operational Cost Estimate
Provide a summary of the operational costs, i.e., costs to keep the system up
From Data Mining the Library Catalogue’s LCA

## Slide 94: 2.1.4 Maintenance Cost Estimate
Provide a summary of maintenance costs if applicable
Should be consistent with Budgets in LCP

## Slide 95: Maintenance Estimate Example
From Data Mining the Library Catalogue’s LCA

## Slide 96: 2.1.5 Estimate of Value Added and Relation to Cost
Provide a summary of cost with and without the product and how much value is added by it. The value added may also describe non-monetary improvements (e.g. quality, response time, etc.) which can be critical in customer support and satisfaction.
Include a Return-On-Investment (ROI) analysis as appropriate.

## Slide 97: Time Spent With Current vs Proposed
In the current environment a Unicorn report can be as large as 2 Gigabytes, but are, on average, no larger than the size of memory and as many as 2000 reports are run in any given month (per the client estimates). Therefore, if an average size of a Unicorn report is 16 MB, and 5,135 pages of information are generated for the client to decipher, and it takes our client 1/2 seconds to scan each page for the information, the time spent deciphering reports takes:
It is hoped that SURG will reduce the size of the reports by at least 1/4, 1/3 or 1/2, which would reduce these numbers to:
From Data Mining the Library Catalogue’s LCA

## Slide 98: ROI Analysis Example (Part I)
From Data Mining the Library Catalogue’s LCA

## Slide 99: ROI Example (Part II)
Using the previous numbers as the Investment Costs, and calculating hours saved for one person as the time it takes to review an original sized report compared to a SURG filtered report of 1/3 the original Unicorn size (See Section 2.1.5.1), the Return On Investment for this project is shown in the table and chart below:
From Data Mining the Library Catalogue’s LCA

## Slide 100: 2.3 Stakeholder Concurrence
Stakeholders may be anybody involved in the development process.
For instance, a developer may argue that a certain response time cannot be achieved in a crisis mode unless nonessential message traffic is eliminated.
Customer may argue that the product does not satisfy his/her win conditions (e.g. cost).

## Slide 101: Stakeholder Concurrence Example
From Data Mining the Library Catalogue’s LCA

## Slide 102: 5. Analysis Results
Identify architectural alternatives and impact
Identify unfeasible architectures or rejected alternatives; document criteria for rejection to avoid having the rejected architectural alternative selected in ignorance at some other point
Describe feasible architectural alternatives which were rejected due to solution constraints on the way that the problem must be solved, such as a mandated technology. Those architectural alternatives may be reconsidered should the solution constraints be relaxed.

## Slide 103: 5.1 Product Features
Discuss advantages to be gained by new (or modified) system
List any limitations of the new system
Discuss any alternative ways in which the new system could be realized

## Slide 104
Sample of Analysis Results from Team 16-1 Spring ’99

## Slide 105: Evaluation of architectural alternatives (a possible approach)
Alternative 1
  Description (ID, name, purpose, scope, boundary)
  Context (System, Context, Stakeholder, Mission, Architecture)
  Views (static, dynamic)
  Impact/Constraint (use Component/COTS/Middleware/Database/Platform/HCI/etc.)
Alternative 2
…
Evaluation of Alternatives

## Slide 106: 5.2 Commercial-off-the-shelf Solutions
List of existing products that should be investigated as potential solutions.
Reference any surveys that have been done on these products.
Is it possible to buy something that already exists or is about to become available? It may not be possible at this stage to say with a lot of confidence, but any likely products should be listed here.
Also consider whether there are products that must not be used.

## Slide 107
Sample of FRD 5.2 (formerly 5.1) from Team 16-1 Spring ’99